## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a support agent, I want to analyze ticket sentiment to prioritize customer issues effectively. | Must | Data preprocessing | Mentor | Completed
Sprint 2 | Sprint 2 | US02 | As a manager, I want to flag critical tickets for escalation to ensure timely resolution. | Must | Sentiment analysis output | Mentor | Completed
Sprint 3 | Sprint 3 | US03 | As a system administrator, I want to automate responses using embeddings and similarity search to save time and ensure consistency. | Should | Pinecone integration | Mentor | Completed
Sprint 1 | Sprint 1 | US04 | As a data scientist, I want to analyze datasets to understand text embedding and clustering better. | Must | None | Mentor | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 70 | 10 | 10 | 10 | 10 | 10 | 8 | 7 | 5 | 3 | 3 | 3 | 3 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Analyze datasets and understand text embedding. | 2024-12-15 | 2024-12-16 | Myself | Data Analysis | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T02 | Conduct prompt engineering to improve sentiment analysis. | 2024-12-17 | 2024-12-19 | Myself | Model Optimization | Completed | 6 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Design and test response automation pipeline (Method 1). | 2024-12-20 | 2024-12-28 | Myself | Pipeline Development | Completed | 16 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T04 | Integrate API endpoints for response automation (Method 2). | 2024-12-29 | 2025-01-11 | Myself | Integration Testing | 3- Completed | 24 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
US05 | T05 | Validate API functionality and conduct end-to-end testing. | 2025-01-12 | 2025-01-25 | Myself | System Testing | 3- Completed | 20 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 1 | Needed labeled data for training. | Added synthetic examples to improve accuracy.
Sprint 1 | 3 | Found inconsistencies in keyword detection logic. | Refined keyword matching using regex patterns.
Sprint 2 | 15 | Delay in embedding generation for large datasets. | Batched processing to optimize performance.
Sprint 2 | 24 | Debugging errors in vector search logic with Pinecone. | Improved Pinecone query handling and caching.
Sprint 3 | 30 | API testing revealed errors in handling edge cases. | Enhanced API error handling for resilience.
Sprint 3 | 32 | Integration testing took longer due to dependencies. | Added automation scripts to streamline testing.
Sprint 3 | 34 | Finalizing workflow showed discrepancies in automation. | Conducted additional debugging and testing.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2024-12-15 | 2024-12-28 | Myself | Adding detailed documentation. | Spending too much time on manual labeling. | Following structured task priorities. | Implemented automation for data preprocessing.
2 | Sprint 2 | 2024-12-29 | 2025-01-11 | Myself | Writing comprehensive test cases for all models. | Delaying minor bug fixes until later. | Continuous API testing after major changes. | Added automated test cases for API endpoints.
3 | Sprint 3 | 2025-01-12 | 2025-01-18 | Myself | Allocating more hours for integration and testing. | Overthinking initial edge cases. | Running workflows end-to-end regularly. | Enhanced logging for better debugging.
4 | Sprint 3 | 2025-01-19 | 2025-01-25 | Myself | Reviewing user feedback on automation. | Working on less critical tickets first. | Prioritizing automation-related workflows. | Addressed key feedback points for improvement.
5 | Sprint 3 | 2025-01-22 | 2025-01-25 | Myself | Collaborating across tasks for final testing. | Overfocusing on metrics over functionality. | Ensuring seamless integration and testing. | Delivered fully functional API workflows.